TERMS OF REFERENCE

CONTRACTING OF A CONSULTANT TO HARMONISE THE SINGLE TRANSPORT DOCUMENT (STD) FOR GOODS IN THE GREATER CARIBBEAN

- CONTEXT.

During the 19th Intersessional Meeting of the Ministerial Council of the Association of Caribbean States (ACS) and the 6th ACS Summit of Heads of State and Government, the International Transit of Goods (TIM) Project was approved as part of the two projects aimed at strengthening the Trade Facilitation process in the Greater Caribbean. Both initiatives are to be financed with resources from the Government of Mexico, via the Mexican International Development Cooperation Agency (AMEXCID).

The TIM project is an initiative that has been implemented since 2008 by the countries involved in the Central American integration process, which has interconnected the customs information systems of those countries, with the support and institutional cooperation of the Mesoamerica Project and with technical and financial assistance from the Inter-American Development Bank (IDB). The implementation process began with the harmonisation of the information contained in the transit declarations of countries, to then link them electronically with a computerised tool that would allow the secure exchange of information among customs authorities prior to the arrival of the goods.

During this phase, approved at the ACS Summits, the TIM Project seeks to broaden its scope of action to include the interconnection of the customs authorities of Greater Caribbean States, sharing the good practices developed previously in the Central American region.

Once this project was approved, two meetings were held with the experts of the customs authorities of the countries of the Greater Caribbean.

- The first was convened in Panama City on April 4, 2014, attended by representatives of the Customs and/or Foreign Trade and Finance Authorities of nineteen (19) ACS Members and Associate Members, namely: Antigua and Barbuda, Barbados, Colombia, Costa Rica, Cuba, Grenada, Guadeloupe, Haiti, Honduras, Jamaica, Martinique, Mexico, Panama, Dominican Republic, St. Kitts and Nevis, St. Vincent and the Grenadines, Saint. Lucia, Saint Maarten and Trinidad and Tobago, to analyse obstacles and identify concrete actions that would help to improve the operating efficiency of customs in the region, with a view to promoting intra-regional trade through the international transit of goods to be developed in the framework of the aforementioned Project.

- The second meeting consisted of a videoconference session, in which there was participation from 12 countries from the Greater Caribbean Region, ACS Members. During the session, the general objectives of the project were outlined through presentations delivered by the Trade Directorate of the ACS and the Tax Administration Service (SAT) of Mexico, a department of the Ministry of Finance and Public Credit. It was also agreed that a document-questionnaire would be circulated to gather national information from ACS States, which would reveal in detail, each country’s characteristics and the adjustments that must be made by each of them in order to adapt to the Central American model, implemented for several years by the Central American Economic Integration System (SIECA).

- OBJECTIVE.

The objective of this Consultation is to conduct an analysis on the international regulations applied in the international transit of goods and determine what is required of each of the member countries of the Greater Caribbean taking part in the TIM Project in order to adjust their national declarations to a regional format for the Single Transit Document (STD).  Subsequently, it must compile all the national requirements into a single document so as to prepare with these inputs, a presentation for countries regarding the critical path that each of them must follow in order to adapt to the regional model of the STD.

  - Specific Objectives.

The Report of the Consultant shall outline:

- A comparative analysis of the international regulations applicable for the International Transit of Goods in the Greater Caribbean region and their viability in view of the implementation of the TIM Project in the Greater Caribbean;

- The national requirements of each participating country in order to adapt to a regional model of the STD, based on the Central American format, including a national and regional critical path toward that end.

- The Proposed Single Transport Document for Greater Caribbean countries, harmonised with the Central American STD;

- The Proposed Regional Regulations on Goods in the Greater Caribbean, using the Central American model.

- The findings of the process, to be presented at an onsite technical meeting on the TIM Project, to be convened upon the completion of this Consultation.

- SCOPE OF WORK.

The Consultant shall:

- Review the international regulations (relevant international conventions, treaties and agreements) applicable to the International Transit of Goods in the Greater Caribbean region.

- Compare the international regulations with the current model applied by the countries of the Central American Integration System (SICA), implemented by the Central American regional STD.

- Review the questionnaires presented by Caribbean countries, following the videoconference session on the TIM Project.

- Analyse the Questionnaires and compare them with the format of the Central American STD, which would allow the compilation of the national requirements (administrative, legal, procedural or technical) for each country to be able to adapt to the regional STD model.

- Prepare a critical path by country, defining the requirements that must be met by each State and conduct a general analysis of the approximate costs involved in harmonising their national declaration with the Central American regional STD model.

- Prepare a Proposal for Regional Regulations on Goods in the Greater Caribbean, using the format applied in Central America, which would allow for harmonisation between the Central American system and that of the Caribbean.

- Prepare a presentation to be delivered during the next onsite meeting of Greater Caribbean Experts on the International Transit of Goods Project, to be convened upon the completion of this Consultation. The consultant shall be notified of the date and venue of this meeting in a timely fashion.

- Make general Recommendations for the subsequent implementation of the TIM Project throughout the Greater Caribbean.

In order to perform this consultation, the consultant may travel to Greater Caribbean States to confirm the findings presented during the period of the contract. The expenses incurred for such travel shall be included in the proposal on the execution of the consultation.

- RESULTS/DELIVERABLES.

The Consultant shall present the following for the due approval of the AMEXCID and the ACS:

| Results | Timeframe for Delivery |
| --- | --- |
| Initial Report that shall include, among other elements, the detailed Methodology proposed and a Work Implementation Plan. | Within two (2) weeks from the signing of the contract. |
| Partial Report on the progress made and the status of the project. | Within six (6) weeks from the signing of the contract. |
| Final Report. | Within twelve (12) weeks from the signing of the contract |

- DURATION.

The terms and conditions of the CONTRACT shall be applied during the period of duration of the CONTRACT, beginning on the date of its signature or the actual date on which the WORK commences, whichever is earlier, for a period of three months.

- FINANCIAL PROPOSAL.

  - The financial proposal must be presented separately and must incorporate all administrative costs, including indirect expenses, printing, dissemination, copying and presentation.

  - The estimated cost of the consultation must not exceed US$40,000.00

- PAYMENT PROGRAMME.

The payment to the Consultant for the submission of the deliverables defined in clause 4.0 above, shall be made according to the following programme:

Acceptance of the Initial Report					10%

Acceptance of the Partial Report 					30%

Acceptance of the Final Report 					60%

Total									100%

- QUALIFICATION AND EXPERIENCE.

Eligible Consultants must have the following qualifications and experience:

  - Degree in law, business administration, specialising in International Law; Law of Treaties; Law of the Sea; Comparative Law; Environmental Law; Multilateral Agreements on the Environment. Any other training in the area of the task assigned will be an asset.

  - Minimum of ten (10) years experience in trade facilitation, international transit of goods.

  - Proficiency and experience in international instruments of maritime trade.

  - Knowledge and work experience in issues affecting the trade environment within the Greater Caribbean Region.

  - Experience in conducting consultation research and preparing analytical and high standard reports.

  - Excellent communication and presentation skills.

  - Proficiency in two (2) of the three official languages of the ACS (English, Spanish and French) will be an asset.

- Additional Information.

This document is merely a request for interest and a proposal for the provision of legal services to the ACS/TC and shall not be interpreted as an offer by the ACS/TC to enter into a service agreement for such duties. Your response shall be considered as an offer to provide said services and not as acceptance of any offer made by the ACS/TC.

- Presentation of the Proposal.

The eligible Consultant(s) must present technical and financial proposals in an electronic format. Proposals must also include, among other elements:

  - Declaration of appropriate experience that would include similar tasks assigned, executed or being executed within the last five (5) years.

  - Measurable goals and objectives, as well as a methodology.

  - Expression of availability to conduct the Consultation during the period September to December 2014.

  - Must include as attachments, accrediting documents such as Curriculum Vitae.

The TIM Project Concept Document is attached (Annex I) to this document and will serve as a guide for the development of the work of the consultant selected.

The Report with the conclusions arrived at during the 1st Meeting of Experts on the International Transit of Goods in the Greater Caribbean (TIM) are included in this document (Annex II).

The Attendance Report (Annex III) contains the list of participants at the videoconference session specifying their countries, names, positions, email addresses and telephone numbers.